CONTRACT NO. ..............................

This contract is concluded on ..................................... between:

ELECTROMONTAJ S.A., a company incorporated under the laws of Romania and having its registered office in Bucharest, 1 Candiano Popescu Street, Romania, registered under No. J40/1099/1990 at the Trade Register, with tax code 566, and VAT RO566, tel: +4021.336.75.96, fax: +40213367492 and e-mail: office@em.ro, represented by Mr. Ionuț-Adrian TANASOAICA, General Manager and Mihaela MARIN, Director Economic, hereinafter referred to as the Buyer,

And

Consortium CKD Blansko - ZDAS for Stejaru HPP, represented by ČKD BLANSKO, a.s., a company incorporated under the law of the Czech Republic and having its registered office in Chladkova 2, Brno, 616 00 Czech Republic, with tax code CZ05156955, E-mail: office@ckdblansko.cz represented by Mr. Yaroslav Okhatrin, hereinafter referred to as the Seller,

Art. 1 Subject matter of the contract

1.1. Under the terms and conditions set out in this contract, the Seller shall sell to the Buyer the equipment referred to in the specifications and shall provide all services related to supervision during installation works and refurbishment of embedded parts , in the quantities and at the prices specified in Annex No. 1 "List of quantities, prices and delivery schedule", for the contract STEJARU signed between the Buyer and S.P.E.E.H. HIDROELECTRICA S.A., hereinafter referred to as the "Beneficiary".

1.2. The equipment supplied shall comply in all respects with the requirements set out in Annex No .2 "Technical Requirements".

1.3. Any delay due to equipment non-compliance with Annex No. 2 "Technical Requirements" shall be the responsibility of the Seller.

1.4 If the Seller does not comply with its obligations and/or responsibilities as set out in present contract, the Buyer has the right to apply any of the provisions of Chapter 13 for the recovery of the damages incurred.

Art. 2 Delivery period, delivery and transport conditions

2.1. The delivery condition is DAP HPP Vidraru site according to Incoterms 2020.

2.2. The delivery time of the equipment will be in accordance with the provisions of Annex No. 1 "List of quantities, prices and delivery schedule".

2.3. Shipment of the equipment shall be made by the Seller only after completion of the inspection and testing and approval procedure (according to art. 8 of this contract)  of the ordered equipment.

2.4. 15 (fifteen) working days prior to shipment, the Seller shall inform the Buyer by e-mail of the equipment specifications and the complete shipment dates.

2.5. The Seller shall choose the safest and fastest means of transport between the factory and the place of unloading in accordance with Incoterms 2020. For avoidance of doubt, it is considered that the access routes to Vidraru HPP (or relevant places of unloading) are in a condition to accommodate the transport loads of the delivered equipment.

2.6. Transport shall be organized in such a way as to comply with the delivery times specified in the contract.

2.7. The Seller has the right to conduct delivery of equipment earlier than the delivery times specified in Annex No. 1 and the Buyer shall accept this.

Art. 3 Labelling, packaging and marking

3.1 Labelling, packaging, and marking of the equipment are included in the price.

3.2. All packaging becomes the property of Buyer.

3.3. The Seller shall be fully responsible for ensuring that the packaging is suitable for long-distance transport and transit to the place of delivery and shall not be exonerated from any loss or damage caused by faulty packaging.

3.4 Equipment must be clearly and properly packed. Markings are to be in accordance with the Buyer's instructions and any legal requirements of the carriers.  In particular, the packing of the equipment must be marked with the contract name, weight (gross/net weight), a description of the contents, with places of delivery and any handling requirements of the Beneficiary. All containers of dangerous goods (and all related documentation) must carry visible and appropriate warnings.

3.5 All packing materials will be considered non-returnable.

Art. 4.  Required documents

4.1. The Seller shall issue and send a set of delivery documents to the Buyer as follows:

4.1.1 - Invoice - 1 original, which must show: number of pieces, unit value, total value of equipment delivered according to Annex 1, payment terms, Seller's address.

4.1.2 - Packing list - 1 original. The packing list must be issued so that it is easy to cross-reference with the FAT/routine test report in terms of number of packages and weight. It must be signed by the Seller.

4.1.3 - CMR

4.1.4 - FAT Report/Routine Test signed by Seller one original for Buyer and one original for Beneficiary.

No shipment will be released until Buyer approval of the FAT Report/Routine Test/Type tests.

4.1.5. - Manufacturer's quality and warranty certificate - 1 original certifying the quality of the equipment, the warranty period according to art. 9 of this contract and the place where the equipment was manufactured or made.

4.1.6. - Certificate of conformity, issued by the Seller, certifying that all equipment supplied under this Contract fully complies with the requirements laid down in the European Union standards and directives to which the equipment/materials in question are subject and that it assumes full responsibility in this respect - 1 original

4.1.7. Certificate of Origin - 1 original

4.1.8 - User manual/Technical book of the equipment in Romanian and English language - 3 printed copies + 1 electronic copy

4.1.9 - Storage instructions in Romanian and English language - 3 printed copies + 1 electronic copy

4.1.10 – Hand over protocol signed by the Buyer

4.1.11. Any modification of the above-mentioned list of documents can be made only with the agreement of the Buyer and the Seller.

Art. 5 Price

5.1. In consideration of the fulfilment by the Seller of the obligations assumed by the Seller under the Contract, the Buyer shall pay the Contract Price in the total amount of xxxx EUR. The unit prices of the Equipment are expressed in EUR and are understood to be firm, i.e. not subject to any indexation, throughout the Contract period for the quantity ordered.

The price of the contract includes the equipment price, the transport price, FAT tests and all marking, labelling and packing costs. Packing is non-returnable.

5.2. The total contract price is detailed in Annex 1 - "List of quantities, prices and delivery terms".

Art. 6 Payment conditions, guarantees, securities

Parties have agreed on the following:

xxxxxx

Payment Security:

6.6. The invoice shall contain all appropriate references to the contract, a detailed breakdown of the equipment invoiced and shall be supported by documentation, as outlined in the articles above.

6.7. The Seller has the following bank accounts:

xxxx

6.8. Any change to the bank account will be communicated unilaterally by the relevant party, as set out in Art. 12, following which an addendum to this contract will be signed.

Art. 7 Approval procedure for Design documentation

7.1 The Seller shall prepare and provide the Buyer with the documentation for approval / endorsement in accordance with the delivery schedule listed in Annex 1 of this Contract.

7.2 Within twenty-one (21) days of receipt by the Buyer of any document requiring the approval, the Buyer shall either return to the Seller a copy of this document with its approval, or notify the Seller in writing of its objections to it, stating the reasons for the rejection and the changes proposed by the Buyer.

7.3 If the Buyer fails to do so within thirty (30) days, from the document receiving date, then the document will be deemed approved.

7.4 If the Buyer rejects the documentation, it will submit specific objections to the documentation, the Seller will review the documentation within fifteen (15) days of receiving the objections and will resend for approval the documents to the Buyer, who has the obligation to analyse them within at most 14 days for documents that are to be endorsed and at most 21 days from receipt for documents that are to be approved (as per Art 7.2.).

7.5 After resolving the comments submitted by the Buyer, the Buyer will not be able to submit further comments to the documentation subject to analysis.

7.6 If the Buyer approves the document subject to some modifications, the Seller will make the requested modification(s), after which the document will be considered approved.

7.7 The parties shall consider a maximum of two rounds of document review. If there are more than two rounds of document review, the Seller has the right to extend the terms for completion of the works and services, if it is not its fault.

Art. 8 Inspection and testing

8.1 The Seller shall permit the Buyer and the authorized representatives of the Beneficiary to carry out any inspections which may reasonably be required and the Seller shall provide all reasonable facilities and assistance at the Seller's premises (such as a meeting room and accompanying English-speaking person for purposes of inspection). Any such inspection shall be mutually agreed and scheduled by the Parties at least 7 working days in advance.

No failure to complain at the time of any such inspection or testing and no approval given during or after such testing or inspection shall constitute a waiver by Buyer of any rights or remedies with respect to the Equipment. Buyer retains the right to reject the Equipment, however such rejection can be done only in case all possible remedies have been attempted and no remedial actions are successful.

8.2 For inspection and testing of the Equipment, the provisions of Inspection and Testing procedures shall be in accordance with the Buyer’s requirements presented in article 8.9 below.

8.3 For FAT accommodation, meals and transport expenses for any inspections or visits of the Buyer and/or the Beneficiary are not included in the Contract Price and are not borne by the Seller.

8.4. In case the tests will be repeated (in case of rejection by the Buyer/Beneficiary for non-compliance to Annex 2), reasonable costs for accommodation, transport and FAT costs incurred for the repetition and reasonable attendance will be borne and paid by the Seller.

8.5 The Seller shall notify by official letter the Buyer 21 days prior to the scheduled date of the final FAT, prepare the equipment for inspection and send to the Buyer also in electronic format the following:

- The relevant FAT program to be performed during the inspection in English language.

- The FAT procedure to be carried out during the inspection in English language.

If inspectors will not attend the FAT inspection, a document will be issued instructing the Seller to do so. Failure to confirm attendance or issue such document within 7 days from the notification letter and/or failure to attend, shall be deemed as approval of conducting of FAT without the presence of the Buyer.

8.6 The Seller shall carry out FAT as presented in article 8.8 below.

8.7. The FAT report will be prepared by the Seller and signed by Seller, Buyer and Beneficiary after FAT. It is the Buyer’s obligation to obtain the Beneficiary’s approval of such report, in case that the Beneficiary will not attend to FAT Seller’s obligation prior to shipment shall be deemed fulfilled upon successful completion of the FAT and the Buyer shall endorse the loading and delivery of the Equipment based on the successful completion of the FAT.

8.8 The Seller must comply with the following requirements:

- The FAT report must be prepared by the Seller in English language.

- the table showing the test results must include the "acceptance criteria” in English language.

- provide a copy of the Calibration Certificate for the equipment used for testing in English language.

- Provide photographs of materials/goods during the test procedure.

8.9. FAT report shall have the following attached:

(a) FAT procedures

(b) factory verification bulletins

(c) technical documentation associated with the equipment

(d) list of measuring devices used and certification of measuring devices

(e) the test scheme applied in the FAT related to each test

The tests to be performed in the FAT are as follows, the price of which is included in the price of the equipment, are according to Tender specification.

8.10. FAT tests shall be carried out for each equipment included in the object of present contract.

8.11. Any intermediary inspections, if present, will follow the same rules, as described above in this Art. 8.

Art. 9 Reception of equipment

9.1. Quantitative acceptance of the equipment shall take place on the date of its delivery, in the presence of a delegate designated by the Seller and the Buyer, by signing the delivery-receipt report of the equipment. The handover-receipt report must contain: date and place of delivery, name of the Buyer's delegate who has received the equipment and the Buyer's signature.

If, at the quantitative acceptance, quantitative shortages and/or physical damage of the equipment are found, they will be recorded in the handover-receipt report, and the Seller is obliged to complete/remedy/replace the missing components of the equipment configuration, at its own expense within a period agreed by the parties.

The quality acceptance of the equipment will take place on the date of commissioning of each individual piece of equipment.

If, on the date of commissioning, the equipment is not functional / has defects and / or inconsistencies in operation compared to the technical specification of the equipment provided in Annex No. 2, the acceptance report will not be signed upon commissioning, and the Seller is obliged to remedy these malfunctions, at its own expense, within a period agreed by the parties. This does not apply, if dysfunction. defects / or inconsistencies are the result of incorrect or negligent treatment or storage of the equipment by the Buyer.

9.2 Any equipment rejected or returned by the Buyer as described in art 9.1 shall be returned to the Seller at the Seller's risk and expense.

9.3 If such defect is not remedied within a time accepted by the Buyer, the Buyer may proceed to replace the defective or damaged equipment at the Seller's risk and expense, provided that the Buyer does so in a reasonable manner.

9.4 Guaranteed and functional parameters are in accordance with the provisions of Annex 2.

Art.10  Equipment warranty

10.1. The Seller warrants the Equipment for 36 months from commissioning, but not more than 48 months from delivery.

10.2. The Seller warrants that, at the time of delivery, the equipment supplied under the contract will be free from defects in design, material or workmanship and will be in accordance with the requirements of Annex 2.

10.3. No claim shall be made for defects if they are the result of incorrect or negligent treatment, stress/strain or storage. The Buyer shall have no claim for defects and/or claims for compensation for that part of the claim which is based solely on the Buyer's or Beneficiary's improper treatment, incorporation, modification or operation of the equipment, and where such claims are based on the Buyer's incorrect instructions to the Seller.

10.4.1. The warranty period shall be extended by a period equal to the period during which the equipment cannot be used due to defective manufacture, materials or design.

10.4.2. If a defective equipment is replaced or part of the equipment is replaced with equipment or part(s) in accordance with provisions of Annex 2, a new warranty period of 36 months from delivery will start to run for this replaced equipment/part(s) of equipment.

10.5. The Seller declares that, in the event of a dispute, it has free and legal possession of all industrial property rights (license, patents, trade secrets, know-how, etc.) relating to the equipment which is the subject of this Contract and guarantees the Buyer against all claims which may be made by third parties in respect of these rights.

10.6. The Seller’s liability excludes any indirect or consequential damages resulting from warranty claims, including but not limited to loss of production, profit, or revenue. Warranty claims must be substantiated by documented evidence of non-compliance with the technical specifications set out in Annex 2.

Art. 11 Insurance

The liability insurance policy for the transport of the equipment to the delivery address shall be borne by the Seller.

Art. 12 Notification

12.1 Unless otherwise expressly provided in the Contract, no notice or other communication from one Party to the other shall have any validity under the Contract unless made in writing by or on behalf of the Party concerned.

12.2 Any notice or other communication to be given by one Party to the other shall be by letter (sent by hand, by post, by registered post or by recorded delivery service) or by electronic mail (confirmed in both cases by letter). Such letters shall be addressed to the other Party in the manner referred to in Condition 12.3.

12.3. For the purposes of art 12.2, the address of each Party is:

- To the Seller:

CKD Blansko a.s.

Address: Chládkova 898/2, 616 00 Brno, Czech Republic

Attention: Mrs. Edita Brandejska, Mr. Yaroslav Okhatrin

E-mail: office@ckdblansko.cz, edita.brandejska@ckdblansko.cz, yaroslav.okhatrin@ckdblansko.cz

(b) For the Buyer:

Electromontaj S.A.

Address: 1 Candiano Popescu Street, Bucharest, 1 Candiano Popescu, Romania

Attention: Stefan TANASE, Florentina  VULPESCU

E-mail: office@em.ro, stefan.tanase@em.ro, florentina.vulpescu@em.ro

12.4 Either Party may change its address for service by giving notice in accordance with this Chapter.

12.5. The Seller shall notify the Buyer within 7 days prior to dispatch of the Equipment of the expected date of dispatch, the expected date of arrival at destination (ETA) and the number of packages, labelling, dimensions, weight and contents in accordance with Art. 4.

Article 13 Penalties and other sanctions

13.1. In the event of failure to meet the contractual deadline for delivery of the equipment, for reasons attributable to the Seller, the Seller shall pay the Buyer a penalty of 0, 1% per each calendar day of the value of the delayed equipment up to delivery of this equipment.

In case the Buyer is late with completion of his obligations in regard to any approvals (including of main materials) and payments within the terms described under this Contract, the Seller has a right to extend the delivery period and such extension shall not be a subject to delay penalty. The extension of the delivery period without penalties is to be understood as follows:

- The delivery will be delayed with the period between the due date of obligation and the effective date of completion of the said obligation only if the Buyer’s delay is less than 10 calendar days

- The delivery will be delayed with a reasonable period if the Buyer’s delay is higher than 11 calendar days but no more than 60 days

13.2 In the event of non-compliance of the equipment with the technical requirements as set out in Annex 2, the Seller shall pay the Buyer a penalty of 0,5% per day of the value of the non-compliant equipment

13.3. If any functional guarantees and /or guaranteed parameters as described in art. 9.4 are not met, the Seller has 2 attempts for remediation in maximum 2 months, After 2 failed attempts for remediation or after the time mentioned before has passed, the Buyer may request payment of  functional guarantees and /or guaranteed parameters damages, representing 10% from price of each equipment for which the guaranteed value was not reached. Such penalty shall be considered the sole remedy for non-fulfilment of the functional guarantees and /or guaranteed parameters.

13.4. The total amount of all such penalties may not exceed 30% of the total contract price. These penalties are irreducible.

13.5  All penalties or expenses for which the Seller is liable to the Buyer may be deducted from any payment due or becoming due.

13.6. In case of non-compliance by the Buyer with the payment obligation mentioned in art. 6.1, the Buyer must pay a late payment penalty to the Seller. The late payment penalty shall be calculated at 0,1% /day of the amount of the outstanding debit.

13.7. In any case, the Seller shall not be liable for any indirect, consequential, punitive, or incidental damages, including, but not limited to, loss of profit, revenue, or production, etc.

13.8. In all cases, the penalty agreed by the Parties and paid by the Seller shall constitute the sole remedy of the Buyer. The Buyer shall not have a right to claim any additional expenses, damages, lost profits, or compensations in excess of the paid penalty.

Art.14. Force majeure

Force majeure must be certified by a competent authority.

14.1 Neither Party shall be liable to the other Party for any delay or non-performance of its obligations under the Contract if such delay or non-performance results from an event of force majeure. Notwithstanding the foregoing, each Party shall use all reasonable efforts to continue to perform its obligations under this Contract during such Force Majeure Event. However, if such event prevents either Party from performing all of its obligations under the Contract for a period in excess of 6 weeks, either Party may terminate the Contract by written notice with immediate effect.

14.2 For the purposes of these Conditions, "Force Majeure" means any event or events beyond the reasonable control of the Party concerned and which cannot be attributed to any act or omission to take preventive action by the Party concerned, including (but not limited to):

[a] war (whether declared or not), armed conflict or serious threat thereof (including but not limited to hostile attack, blockade, military embargo), hostilities, invasion, act of a foreign enemy, large-scale military mobilization;

[b] civil war, revolt, rebellion and revolution, military or usurped power, insurrection,

[c] act of terrorism, sabotage.

[d] act of authority, legal or illegal, compliance with a law or governmental order, rule, regulation or directive, curfew restriction, expropriation, forced acquisition, confiscation of works, requisition, nationalization.

[e] Act of God, plague, epidemic, natural disaster, such as, but not limited to, severe storm, cyclone, typhoon, hurricane, tornado, blizzard, earthquake, volcanic activity, landslide, tidal wave, tsunami, flood, lightning damage or destruction, drought.

[f] acts of cyber-terrorism, cyber-attacks, hacking, or other significant disruptions to digital infrastructure;

[i] nuclear, chemical, or biological contamination.

14.3. In the event of a dispute, the party claiming to be affected by force majeure shall bear the burden of proving that it has been affected.

14.4. The party invoking this clause is obliged to take all reasonable steps to limit the effect of the impediment or event invoked on the performance of its contractual obligations.

14.5 Notice of such Force Majeure must be given in writing to the other party within five (5) business days of the occurrence of the cause invoked, then the obligations of the affected party shall be suspended so long as such inability continues due to such Force Majeure. In addition, the party invoking the Force Majeure must notify the other party in writing of its resolution within five (5) business days of the resolution.

14.6 For the avoidance of doubt, it is hereby expressly declared that the only events which shall provide relief from liability for non-performance or delay in performance of the contract are any events which qualify as Force Majeure under this contract and any event that exists at the moment of the contract signature.

Art.15. Disputes

All disputes of any nature whatsoever related to or in connection with this contract, which cannot be settled amicably, shall be submitted to arbitration in accordance with the Rules of Conciliation and Arbitration of the International Commercial Arbitration Court of the Chamber of Commerce and Industry of Bucharest, Romania.

The seat of the arbitration shall be in Bucharest and the language used shall be English.

Art. 16 Termination of contract

16.1. The contract may be terminated by agreement of both parties.

16.2 The Buyer has the right to consider the Contract to be terminated as of right, with 30 days written notice, without the intervention of the court, without putting the Seller in default or fulfilling any other formality, on the basis of a unilateral declaration of termination, in the following cases:

-In the event the Seller failure to comply with the delivery obligation according to Annex 1

-In case of failure to comply with the obligations set out in Art. 8

-If the Seller has been convicted by a final judgment of the courts for a professional conduct offence if he has been convicted by a final judgment of the courts, if he has been convicted by a final judgment of the courts for fraud, corruption, involvement in a final judgment of the courts for fraud, corruption, involvement in a criminal organization or for any other illegal activity against the financial interests of Romania and the European Community.

-If the Seller consistently breaches the obligations assumed by this Contract, after repeated notifications.

16.3. The Buyer has the right to terminate the Contract if:

- The Seller has been convicted by a final judgment of the courts for a professional conduct offence, if he has been convicted by a final judgment of the courts for fraud, corruption, involvement in a final judgment of the courts for fraud, corruption, involvement in a criminal organization or for any other illegal activity against the financial interests of Romania and the European Community.

16.4. The Seller has the right to terminate the contract, with a written notice of remedy of 45 days, if the Buyer does not comply with its payment obligation within the terms and conditions of the contract.

16.5. The Seller has the right to terminate the contract if:

-if the Buyer has been convicted by a final judgment of the courts for a professional conduct offence, if he has been convicted by a final judgment of the courts for fraud, corruption, involvement in a final judgment of the courts for fraud, corruption, involvement in a criminal organisation or for any other illegal activity against the financial interests of Romania and the European Community.

16.6 Regardless of the method of termination of the contract, such termination shall not affect the obligations already due to the parties.

16.7 Integrity and anti-corruption: Each party shall conduct its business with honesty and integrity and demonstrate the highest standards of business ethics. Each Party shall not engage in bribery, corruption or other unethical or illegal practices, whether in dealings with government officials (which includes government employees or officials at any level, employees or officials of government-controlled or government-owned entities, employees or officials of public international organizations, and political officials or candidates or any person acting on behalf of such a person), political parties or other persons, including persons in the private sector. This includes, directly or indirectly, paying, offering, giving, promising or authorising money or anything else of value to anyone to try to obtain an improper or improper advantage. This also includes any unethical business activities or arrangements between the Buyer and any employee of the Beneficiary or any other company or individual.

Each party agrees and acknowledges that, in the conduct of its activities, it will comply with and cause its affiliates, agents and authorized employees to comply with all applicable laws and regulations with respect to the activities contemplated by this Contract.

16.8. Before exercising any right to terminate this Contract, either Party shall first engage in good-faith negotiations with the other Party to resolve any disputes or issues that may have arisen. The parties explicitly states, that they consider the termination of this contract as a last resort in case that all negotiations leading to amicable resolve of the dispute fails, and they do not agree otherwise. Only if such negotiations fail to produce a mutually acceptable solution within thirty (30) days may either Party proceed with termination under the terms specified in this Contract.

Article 17 Final Provisions

17.1. Any additions or amendments to this Contract shall be valid and binding between the parties hereto if expressly set forth in written documents (contract addendum) dated and signed by both parties.

Accordingly, any deviation from this Contract, even if repeated and uncontested by the party entitled, shall be considered as mere tolerance.

17.2 All correspondence under or in connection with this Contract shall be in English.

17.3 All documents prior to the signing of this Contract, signed by either or both parties, relating to this Contract shall be null and void after the signing of this Contract.

17.4. The Contract shall come into force on the Commencement Date and shall expire on the date of termination of the Warranty Period, subject to the settlement of all claims of the Buyer. "Commencement Date" means the date of signature of the Contract.

17.5. Annex no. 1,2 and 3 form an integral part of this Contract.

17.6 If any provision of the Contract is declared invalid, illegal, or unenforceable for any reason by a court of competent jurisdiction, such provision shall be struck out and the remainder of the provisions of the Contract shall continue in effect as if the Contract had been executed with the invalid, illegal or unenforceable provision struck out.

17.7. The Seller warrants and represents that:

(a) Seller has full capacity and authority and all necessary consents to enter into and perform this Contract and that this Contract is executed by a duly authorized representative of Seller.

(b) Seller shall perform its obligations under this Contract with all due skill, care and diligence, including but not limited to good industry practice and (without limiting the generality of these Conditions) in accordance with its own established internal procedures.

(c) the Equipment shall be reasonably satisfactory to the Buyer.

(d) the Equipment shall comply in all respects with any technical specification approved by the Buyer/Beneficiary all Equipment supplied shall be within normal industrial quality limits;

(e) the Equipment must perform in accordance with the relevant Technical Specifications and must comply with the requirements of the Specifications and any particulars specified in this Contract.

(f) the equipment must comply in all respects with the requirements of Annex 2 and applicable EU norms and regulations

(g) the equipment shall be free from defects in design, materials and workmanship and shall be fit and sufficient for all purposes for which such equipment is ordinarily used and for any special purpose brought to the Seller's attention by the Seller.

(h) all obligations of the Seller under the Contract shall be performed and performed by Personnel of appropriate experience, skill and training, with all due skill, care and diligence.

17.8. NA

This Contract has been drawn up and signed in 2 originals, one original for the Buyer and one original for the Seller, on the date of..............

| Buyer: ELECTROMONTAJ S.A Managing Director Ionut-Adrian TANASOAICA Economic Director Mihaela MARIN Business Development Director Cosmin MITU Project Manager Stefan TANASE Procurement Director Florentina VULPESCU Legal Director Alina STRATON CRISTIADIS | Seller: CKD Blansko a.s. General Manager Yaroslav Okhatrin |
| --- | --- |